## Dashboard
Upcoming |  |  | Project Plan
Issues | Owner | Open Date
Closed expansion slots | Lucius Fox | 2023-04-18
Missing template files | James Gordon | 2023-04-19
Closed expansion slots | Lucius Fox | 2023-04-19
Battery status screen are not working | Bruce Wayne | 2023-04-20
Closed monitoring meter | Joker | 2023-04-22
Closed expansion slots | Barbara Gordon | 2023-04-25
Broken expansion slots | James Gordon | 2023-04-26
Missing expansion slots | Bane | 2023-04-27
Slow template files | Richard Grayson | 2023-04-28
Broken template files | James Gordon | 2023-04-30
Our People
Person | Issues | Activities
Alfred Pennyworth | 2 | 9
Bane | 1 | 11
Barbara Gordon | 1 | 16
Bruce Wayne | 3 | 6
Harley Quinn | 2 | 6
James Gordon | 5 | 11
Joker | 4 | 8
Lucius Fox | 4 | 11
Richard Grayson | 2 | 12
Selina Kyle | 1 | 10
Today's Date
17-Apr-23
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Activities Ongoing
29
Status Dashboard
Project Management
Days to Go
53
Issues Pending
23

## Gantt Chart
 | time axis 2023-04-03 to 2023-06-07
 | time axis 2023-04-03 to 2023-06-07
 | time axis 2023-04-03 to 2023-06-07
Category | Activity | Person | Start | End | %
Deployment |  |  | 2023-03-01 | 2023-06-04 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
| Act 002 | Harley Quinn | 2023-03-01 | 2023-03-11 | 70% | 0.7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 012 | Joker | 2023-03-08 | 2023-03-14 | 88% | 0.88 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 016 | Selina Kyle | 2023-03-13 | 2023-03-19 | 99% | 0.99 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 019 | Joker | 2023-03-17 | 2023-03-22 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 022 | Harley Quinn | 2023-03-18 | 2023-03-21 | 44% | 0.44 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 025 | James Gordon | 2023-03-21 | 2023-03-25 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 027 | James Gordon | 2023-03-24 | 2023-03-28 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 028 | Bane | 2023-03-24 | 2023-04-02 | 79% | 0.79 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 032 | Joker | 2023-03-29 | 2023-04-02 | 22% | 0.22 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 038 | Bane | 2023-04-02 | 2023-04-05 | 100% | 1 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 044 | Richard Grayson | 2023-04-07 | 2023-04-15 | 45% | 0.45 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 049 | Barbara Gordon | 2023-04-13 | 2023-04-19 | 79% | 0.79 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 060 | Richard Grayson | 2023-04-26 | 2023-05-06 | 25% | 0.25 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 068 | Joker | 2023-05-04 | 2023-05-13 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 069 | Joker | 2023-05-05 | 2023-05-12 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 075 | Selina Kyle | 2023-05-11 | 2023-05-14 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 076 | Barbara Gordon | 2023-05-12 | 2023-05-19 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 079 | Barbara Gordon | 2023-05-14 | 2023-05-19 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 088 | Bane | 2023-05-22 | 2023-05-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 096 | Barbara Gordon | 2023-06-01 | 2023-06-04 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE
Design |  |  | 2023-03-01 | 2023-06-06 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
| Act 001 | Barbara Gordon | 2023-03-01 | 2023-03-04 | 59% | 0.59 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 005 | Richard Grayson | 2023-03-05 | 2023-03-12 | 75% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 006 | Bruce Wayne | 2023-03-06 | 2023-03-16 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 013 | Lucius Fox | 2023-03-09 | 2023-03-13 | 51% | 0.51 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 039 | Lucius Fox | 2023-04-03 | 2023-04-09 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 041 | Richard Grayson | 2023-04-03 | 2023-04-06 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 047 | James Gordon | 2023-04-10 | 2023-04-13 | 65% | 0.65 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 050 | Joker | 2023-04-14 | 2023-04-23 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 052 | Bruce Wayne | 2023-04-17 | 2023-04-23 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 053 | Lucius Fox | 2023-04-19 | 2023-04-24 | 59% | 0.59 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 057 | Alfred Pennyworth | 2023-04-25 | 2023-05-04 | 62% | 0.62 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 062 | Bane | 2023-04-30 | 2023-05-08 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 064 | Lucius Fox | 2023-05-01 | 2023-05-09 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 071 | Bruce Wayne | 2023-05-07 | 2023-05-12 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 074 | Bane | 2023-05-10 | 2023-05-20 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 077 | Richard Grayson | 2023-05-13 | 2023-05-20 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 081 | Harley Quinn | 2023-05-16 | 2023-05-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 082 | Richard Grayson | 2023-05-16 | 2023-05-20 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 091 | Joker | 2023-05-25 | 2023-05-28 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 097 | Lucius Fox | 2023-06-01 | 2023-06-04 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE
| Act 099 | Barbara Gordon | 2023-06-03 | 2023-06-06 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE
Development |  |  | 2023-03-07 | 2023-05-27 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 007 | Barbara Gordon | 2023-03-07 | 2023-03-15 | 78% | 0.78 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 011 | Selina Kyle | 2023-03-08 | 2023-03-18 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 017 | Barbara Gordon | 2023-03-15 | 2023-03-19 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 021 | Alfred Pennyworth | 2023-03-18 | 2023-03-23 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 023 | James Gordon | 2023-03-19 | 2023-03-26 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 031 | Bane | 2023-03-27 | 2023-04-06 | 76% | 0.76 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 036 | Bane | 2023-03-30 | 2023-04-07 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 045 | Bruce Wayne | 2023-04-08 | 2023-04-14 | 92% | 0.92 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 054 | Barbara Gordon | 2023-04-21 | 2023-04-27 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 058 | Selina Kyle | 2023-04-25 | 2023-05-01 | 72% | 0.72 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 059 | Harley Quinn | 2023-04-25 | 2023-05-01 | 45% | 0.45 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 063 | Lucius Fox | 2023-04-30 | 2023-05-03 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 065 | Alfred Pennyworth | 2023-05-01 | 2023-05-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 070 | James Gordon | 2023-05-05 | 2023-05-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE
| Act 085 | James Gordon | 2023-05-18 | 2023-05-27 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 086 | Richard Grayson | 2023-05-19 | 2023-05-27 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Requirements |  |  | 2023-03-03 | 2023-06-09 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| Act 003 | Richard Grayson | 2023-03-03 | 2023-03-07 | 62% | 0.62 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 004 | Selina Kyle | 2023-03-04 | 2023-03-14 | 60% | 0.6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 009 | Alfred Pennyworth | 2023-03-07 | 2023-03-11 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 010 | Alfred Pennyworth | 2023-03-08 | 2023-03-13 | 27% | 0.27 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 014 | Harley Quinn | 2023-03-11 | 2023-03-15 | 95% | 0.95 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 018 | Harley Quinn | 2023-03-16 | 2023-03-22 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 020 | Alfred Pennyworth | 2023-03-18 | 2023-03-24 | 83% | 0.83 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 034 | Selina Kyle | 2023-03-29 | 2023-04-06 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 035 | James Gordon | 2023-03-29 | 2023-04-06 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 037 | Richard Grayson | 2023-04-01 | 2023-04-04 | 100% | 1 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 040 | Lucius Fox | 2023-04-03 | 2023-04-11 | 27% | 0.27 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 043 | Barbara Gordon | 2023-04-05 | 2023-04-11 | 84% | 0.84 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 048 | Bruce Wayne | 2023-04-11 | 2023-04-15 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 056 | Joker | 2023-04-25 | 2023-04-29 | 96% | 0.96 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 061 | James Gordon | 2023-04-28 | 2023-05-03 | 87% | 0.87 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 067 | Barbara Gordon | 2023-05-02 | 2023-05-10 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 072 | Richard Grayson | 2023-05-07 | 2023-05-13 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 078 | Selina Kyle | 2023-05-13 | 2023-05-22 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 084 | Alfred Pennyworth | 2023-05-18 | 2023-05-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 087 | Bane | 2023-05-20 | 2023-05-28 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 090 | Barbara Gordon | 2023-05-23 | 2023-05-28 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 092 | Bane | 2023-05-27 | 2023-06-05 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
| Act 093 | James Gordon | 2023-05-29 | 2023-06-02 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
| Act 094 | Lucius Fox | 2023-05-30 | 2023-06-03 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
| Act 095 | Selina Kyle | 2023-05-31 | 2023-06-08 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| Act 100 | James Gordon | 2023-06-05 | 2023-06-09 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
Testing |  |  | 2023-03-07 | 2023-06-09 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| Act 008 | Barbara Gordon | 2023-03-07 | 2023-03-16 | 61% | 0.61 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 015 | Bane | 2023-03-13 | 2023-03-23 | 70% | 0.7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 024 | Lucius Fox | 2023-03-19 | 2023-03-24 | 88% | 0.88 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 026 | Selina Kyle | 2023-03-23 | 2023-03-30 | 70% | 0.7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 029 | Bruce Wayne | 2023-03-25 | 2023-03-31 | 100% | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 030 | Richard Grayson | 2023-03-27 | 2023-04-04 | 100% | 1 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 033 | Alfred Pennyworth | 2023-03-29 | 2023-04-04 | 67% | 0.67 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 042 | James Gordon | 2023-04-03 | 2023-04-09 | 100% | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 046 | Bane | 2023-04-09 | 2023-04-19 | 66% | 0.66 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 051 | Alfred Pennyworth | 2023-04-15 | 2023-04-22 | 96% | 0.96 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 055 | Barbara Gordon | 2023-04-23 | 2023-04-26 | 21% | 0.21 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 066 | Richard Grayson | 2023-05-02 | 2023-05-06 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 073 | Selina Kyle | 2023-05-09 | 2023-05-17 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 080 | Barbara Gordon | 2023-05-15 | 2023-05-21 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 089 | Lucius Fox | 2023-05-23 | 2023-05-26 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 098 | Lucius Fox | 2023-06-01 | 2023-06-09 | 0% | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Teams-data
Person | Team
Bruce Wayne | Code Wizards
James Gordon | Code Wizards
Alfred Pennyworth | Code Wizards
Bane | Code Wizards
Selina Kyle | Code Wizards
Harley Quinn | Cyber Surfers
Barbara Gordon | Cyber Surfers
Richard Grayson | Cyber Surfers
Joker | Cyber Surfers
Lucius Fox | Cyber Surfers

## Activity-data
Activity | Category | Owner | Start Date | End Date | % Done
Act 001 | Design | Barbara Gordon | 2023-03-01 | 2023-03-04 | 59%
Act 002 | Deployment | Harley Quinn | 2023-03-01 | 2023-03-11 | 70%
Act 003 | Requirements | Richard Grayson | 2023-03-03 | 2023-03-07 | 62%
Act 004 | Requirements | Selina Kyle | 2023-03-04 | 2023-03-14 | 60%
Act 005 | Design | Richard Grayson | 2023-03-05 | 2023-03-12 | 75%
Act 006 | Design | Bruce Wayne | 2023-03-06 | 2023-03-16 | 100%
Act 007 | Development | Barbara Gordon | 2023-03-07 | 2023-03-15 | 78%
Act 008 | Testing | Barbara Gordon | 2023-03-07 | 2023-03-16 | 61%
Act 009 | Requirements | Alfred Pennyworth | 2023-03-07 | 2023-03-11 | 100%
Act 010 | Requirements | Alfred Pennyworth | 2023-03-08 | 2023-03-13 | 27%
Act 011 | Development | Selina Kyle | 2023-03-08 | 2023-03-18 | 100%
Act 012 | Deployment | Joker | 2023-03-08 | 2023-03-14 | 88%
Act 013 | Design | Lucius Fox | 2023-03-09 | 2023-03-13 | 51%
Act 014 | Requirements | Harley Quinn | 2023-03-11 | 2023-03-15 | 95%
Act 015 | Testing | Bane | 2023-03-13 | 2023-03-23 | 70%
Act 016 | Deployment | Selina Kyle | 2023-03-13 | 2023-03-19 | 99%
Act 017 | Development | Barbara Gordon | 2023-03-15 | 2023-03-19 | 100%
Act 018 | Requirements | Harley Quinn | 2023-03-16 | 2023-03-22 | 100%
Act 019 | Deployment | Joker | 2023-03-17 | 2023-03-22 | 100%
Act 020 | Requirements | Alfred Pennyworth | 2023-03-18 | 2023-03-24 | 83%
Act 021 | Development | Alfred Pennyworth | 2023-03-18 | 2023-03-23 | 100%
Act 022 | Deployment | Harley Quinn | 2023-03-18 | 2023-03-21 | 44%
Act 023 | Development | James Gordon | 2023-03-19 | 2023-03-26 | 100%
Act 024 | Testing | Lucius Fox | 2023-03-19 | 2023-03-24 | 88%
Act 025 | Deployment | James Gordon | 2023-03-21 | 2023-03-25 | 100%
Act 026 | Testing | Selina Kyle | 2023-03-23 | 2023-03-30 | 70%
Act 027 | Deployment | James Gordon | 2023-03-24 | 2023-03-28 | 100%
Act 028 | Deployment | Bane | 2023-03-24 | 2023-04-02 | 79%
Act 029 | Testing | Bruce Wayne | 2023-03-25 | 2023-03-31 | 100%
Act 030 | Testing | Richard Grayson | 2023-03-27 | 2023-04-04 | 100%
Act 031 | Development | Bane | 2023-03-27 | 2023-04-06 | 76%
Act 032 | Deployment | Joker | 2023-03-29 | 2023-04-02 | 22%
Act 033 | Testing | Alfred Pennyworth | 2023-03-29 | 2023-04-04 | 67%
Act 034 | Requirements | Selina Kyle | 2023-03-29 | 2023-04-06 | 100%
Act 035 | Requirements | James Gordon | 2023-03-29 | 2023-04-06 | 100%
Act 036 | Development | Bane | 2023-03-30 | 2023-04-07 | 100%
Act 037 | Requirements | Richard Grayson | 2023-04-01 | 2023-04-04 | 100%
Act 038 | Deployment | Bane | 2023-04-02 | 2023-04-05 | 100%
Act 039 | Design | Lucius Fox | 2023-04-03 | 2023-04-09 | 100%
Act 040 | Requirements | Lucius Fox | 2023-04-03 | 2023-04-11 | 27%
Act 041 | Design | Richard Grayson | 2023-04-03 | 2023-04-06 | 100%
Act 042 | Testing | James Gordon | 2023-04-03 | 2023-04-09 | 100%
Act 043 | Requirements | Barbara Gordon | 2023-04-05 | 2023-04-11 | 84%
Act 044 | Deployment | Richard Grayson | 2023-04-07 | 2023-04-15 | 45%
Act 045 | Development | Bruce Wayne | 2023-04-08 | 2023-04-14 | 92%
Act 046 | Testing | Bane | 2023-04-09 | 2023-04-19 | 66%
Act 047 | Design | James Gordon | 2023-04-10 | 2023-04-13 | 65%
Act 048 | Requirements | Bruce Wayne | 2023-04-11 | 2023-04-15 | 100%
Act 049 | Deployment | Barbara Gordon | 2023-04-13 | 2023-04-19 | 79%
Act 050 | Design | Joker | 2023-04-14 | 2023-04-23 | 100%
Act 051 | Testing | Alfred Pennyworth | 2023-04-15 | 2023-04-22 | 96%
Act 052 | Design | Bruce Wayne | 2023-04-17 | 2023-04-23 | 100%
Act 053 | Design | Lucius Fox | 2023-04-19 | 2023-04-24 | 59%
Act 054 | Development | Barbara Gordon | 2023-04-21 | 2023-04-27 | 100%
Act 055 | Testing | Barbara Gordon | 2023-04-23 | 2023-04-26 | 21%
Act 056 | Requirements | Joker | 2023-04-25 | 2023-04-29 | 96%
Act 057 | Design | Alfred Pennyworth | 2023-04-25 | 2023-05-04 | 62%
Act 058 | Development | Selina Kyle | 2023-04-25 | 2023-05-01 | 72%
Act 059 | Development | Harley Quinn | 2023-04-25 | 2023-05-01 | 45%
Act 060 | Deployment | Richard Grayson | 2023-04-26 | 2023-05-06 | 25%
Act 061 | Requirements | James Gordon | 2023-04-28 | 2023-05-03 | 87%
Act 062 | Design | Bane | 2023-04-30 | 2023-05-08 | 100%
Act 063 | Development | Lucius Fox | 2023-04-30 | 2023-05-03 | 0%
Act 064 | Design | Lucius Fox | 2023-05-01 | 2023-05-09 | 0%
Act 065 | Development | Alfred Pennyworth | 2023-05-01 | 2023-05-08 | 0%
Act 066 | Testing | Richard Grayson | 2023-05-02 | 2023-05-06 | 0%
Act 067 | Requirements | Barbara Gordon | 2023-05-02 | 2023-05-10 | 0%
Act 068 | Deployment | Joker | 2023-05-04 | 2023-05-13 | 0%
Act 069 | Deployment | Joker | 2023-05-05 | 2023-05-12 | 0%
Act 070 | Development | James Gordon | 2023-05-05 | 2023-05-08 | 0%
Act 071 | Design | Bruce Wayne | 2023-05-07 | 2023-05-12 | 0%
Act 072 | Requirements | Richard Grayson | 2023-05-07 | 2023-05-13 | 0%
Act 073 | Testing | Selina Kyle | 2023-05-09 | 2023-05-17 | 0%
Act 074 | Design | Bane | 2023-05-10 | 2023-05-20 | 0%
Act 075 | Deployment | Selina Kyle | 2023-05-11 | 2023-05-14 | 0%
Act 076 | Deployment | Barbara Gordon | 2023-05-12 | 2023-05-19 | 0%
Act 077 | Design | Richard Grayson | 2023-05-13 | 2023-05-20 | 0%
Act 078 | Requirements | Selina Kyle | 2023-05-13 | 2023-05-22 | 0%
Act 079 | Deployment | Barbara Gordon | 2023-05-14 | 2023-05-19 | 0%
Act 080 | Testing | Barbara Gordon | 2023-05-15 | 2023-05-21 | 0%
Act 081 | Design | Harley Quinn | 2023-05-16 | 2023-05-26 | 0%
Act 082 | Design | Richard Grayson | 2023-05-16 | 2023-05-20 | 0%
Act 083 | Development | Barbara Gordon | 2023-05-17 | 2023-05-25 | 0%
Act 084 | Requirements | Alfred Pennyworth | 2023-05-18 | 2023-05-26 | 0%
Act 085 | Development | James Gordon | 2023-05-18 | 2023-05-27 | 0%
Act 086 | Development | Richard Grayson | 2023-05-19 | 2023-05-27 | 0%
Act 087 | Requirements | Bane | 2023-05-20 | 2023-05-28 | 0%
Act 088 | Deployment | Bane | 2023-05-22 | 2023-05-26 | 0%
Act 089 | Testing | Lucius Fox | 2023-05-23 | 2023-05-26 | 0%
Act 090 | Requirements | Barbara Gordon | 2023-05-23 | 2023-05-28 | 0%
Act 091 | Design | Joker | 2023-05-25 | 2023-05-28 | 0%
Act 092 | Requirements | Bane | 2023-05-27 | 2023-06-05 | 0%
Act 093 | Requirements | James Gordon | 2023-05-29 | 2023-06-02 | 0%
Act 094 | Requirements | Lucius Fox | 2023-05-30 | 2023-06-03 | 0%
Act 095 | Requirements | Selina Kyle | 2023-05-31 | 2023-06-08 | 0%
Act 096 | Deployment | Barbara Gordon | 2023-06-01 | 2023-06-04 | 0%
Act 097 | Design | Lucius Fox | 2023-06-01 | 2023-06-04 | 0%
Act 098 | Testing | Lucius Fox | 2023-06-01 | 2023-06-09 | 0%
Act 099 | Design | Barbara Gordon | 2023-06-03 | 2023-06-06 | 0%
Act 100 | Requirements | James Gordon | 2023-06-05 | 2023-06-09 | 0%

## Issue-data
Issue | Assigned to | Priority | Date opened | Date Closed
Keyboard scanner won't open up | Bruce Wayne | High | 2023-04-02
Server email folder not responding | Harley Quinn | High | 2023-04-03
Keyboard scanner not responding | Joker | High | 2023-04-04
Keyboard scanner won't open up | Alfred Pennyworth | Low | 2023-04-05 | 2021-04-08
Keyboard scanner not responding | Richard Grayson | Low | 2023-04-05
Missing monitoring meter | Lucius Fox | Low | 2023-04-06
Server email folder are not working | Bruce Wayne | Low | 2023-04-07
User specifications are not working | James Gordon | Low | 2023-04-07
Missing interaction effects | Joker | High | 2023-04-08
Battery status screen not responding | Selina Kyle | High | 2023-04-09
Broken template files | Lucius Fox | Low | 2023-04-11 | 2021-04-14
Closed template files | Harley Quinn | Low | 2023-04-12
Keyboard scanner won't open up | James Gordon | Low | 2023-04-14
User specifications is blended | Joker | Low | 2023-04-17
Missing interaction effects | Alfred Pennyworth | High | 2023-04-17
Closed expansion slots | Lucius Fox | High | 2023-04-18
Missing template files | James Gordon | Low | 2023-04-19
Closed expansion slots | Lucius Fox | Low | 2023-04-19
Battery status screen are not working | Bruce Wayne | Low | 2023-04-20
Closed monitoring meter | Joker | Low | 2023-04-22
Closed expansion slots | Barbara Gordon | Low | 2023-04-25
Broken expansion slots | James Gordon | High | 2023-04-26
Missing expansion slots | Bane | High | 2023-04-27
Slow template files | Richard Grayson | Low | 2023-04-28
Broken template files | James Gordon | High | 2023-04-30

## Calculations
Category | Activity | Min of Start Date | Max of End Date | Scenario
Deployment |  | 2023-03-01 | 2023-06-04 | Today's Date | minus | Start Date | Start Date (value)
| Act 002 | 2023-03-01 | 2023-03-11 | 2023-04-17 | 14 | 2023-04-03 | 2023-04-03 |  |  |  | What to show in the Dashboard |  |  | Row Labels | Count of Assigned to | Count of Owner
| Act 012 | 2023-03-08 | 2023-03-14 | [7 empty] | Issues | Owner | Open Date | Alfred Pennyworth | 2 | 9
| Act 016 | 2023-03-13 | 2023-03-19 | Choices |  | 2 |  |  |  |  | Closed expansion slots | Lucius Fox | 2023-04-18 | Bane | 1 | 11
| Act 019 | 2023-03-17 | 2023-03-22 | Activities | [6 empty] | Missing template files | James Gordon | 2023-04-19 | Barbara Gordon | 1 | 16
| Act 022 | 2023-03-18 | 2023-03-21 | Issues | [6 empty] | Closed expansion slots | Lucius Fox | 2023-04-19 | Bruce Wayne | 3 | 6
| Act 025 | 2023-03-21 | 2023-03-25 | [7 empty] | Battery status screen are not working | Bruce Wayne | 2023-04-20 | Harley Quinn | 2 | 6
| Act 027 | 2023-03-24 | 2023-03-28 |  |  |  |  | Upcoming Activities (top 10) |  |  | Closed monitoring meter | Joker | 2023-04-22 | James Gordon | 5 | 11
| Act 028 | 2023-03-24 | 2023-04-02 |  |  |  |  | Activity | Category | Start Date | Closed expansion slots | Barbara Gordon | 2023-04-25 | Joker | 4 | 8
| Act 032 | 2023-03-29 | 2023-04-02 |  |  |  |  | Act 053 | Design | 2023-04-19 | Broken expansion slots | James Gordon | 2023-04-26 | Lucius Fox | 4 | 11
| Act 038 | 2023-04-02 | 2023-04-05 | Calculations for Dashboard Cards |  |  |  | Act 054 | Development | 2023-04-21 | Missing expansion slots | Bane | 2023-04-27 | Richard Grayson | 2 | 12
| Act 044 | 2023-04-07 | 2023-04-15 | Days Left | 53 |  |  | Act 055 | Testing | 2023-04-23 | Slow template files | Richard Grayson | 2023-04-28 | Selina Kyle | 1 | 10
| Act 049 | 2023-04-13 | 2023-04-19 | Activities Pending | 29 |  |  | Act 056 | Requirements | 2023-04-25 | Broken template files | James Gordon | 2023-04-30
| Act 060 | 2023-04-26 | 2023-05-06 | Issues Pending | 23 |  |  | Act 057 | Design | 2023-04-25
| Act 068 | 2023-05-04 | 2023-05-13 |  |  |  |  | Act 058 | Development | 2023-04-25
| Act 069 | 2023-05-05 | 2023-05-12 |  |  |  |  | Act 059 | Development | 2023-04-25
| Act 075 | 2023-05-11 | 2023-05-14 |  |  |  |  | Act 060 | Deployment | 2023-04-26
| Act 076 | 2023-05-12 | 2023-05-19 |  |  |  |  | Act 061 | Requirements | 2023-04-28
| Act 079 | 2023-05-14 | 2023-05-19 |  |  |  |  | Act 062 | Design | 2023-04-30
| Act 088 | 2023-05-22 | 2023-05-26
| Act 096 | 2023-06-01 | 2023-06-04 |  |  |  |  | Upcoming Issues(top 10)
Design |  | 2023-03-01 | 2023-06-06 |  |  |  |  | Issues | Owner | Open Date
| Act 001 | 2023-03-01 | 2023-03-04 |  |  |  |  | Closed expansion slots | Lucius Fox | 2023-04-18
| Act 005 | 2023-03-05 | 2023-03-12 |  |  |  |  | Missing template files | James Gordon | 2023-04-19
| Act 006 | 2023-03-06 | 2023-03-16 |  |  |  |  | Closed expansion slots | Lucius Fox | 2023-04-19
| Act 013 | 2023-03-09 | 2023-03-13 |  |  |  |  | Battery status screen are not working | Bruce Wayne | 2023-04-20
| Act 039 | 2023-04-03 | 2023-04-09 |  |  |  |  | Closed monitoring meter | Joker | 2023-04-22
| Act 041 | 2023-04-03 | 2023-04-06 |  |  |  |  | Closed expansion slots | Barbara Gordon | 2023-04-25
| Act 047 | 2023-04-10 | 2023-04-13 |  |  |  |  | Broken expansion slots | James Gordon | 2023-04-26
| Act 050 | 2023-04-14 | 2023-04-23 |  |  |  |  | Missing expansion slots | Bane | 2023-04-27
| Act 052 | 2023-04-17 | 2023-04-23 |  |  |  |  | Slow template files | Richard Grayson | 2023-04-28
| Act 053 | 2023-04-19 | 2023-04-24 |  |  |  |  | Broken template files | James Gordon | 2023-04-30
| Act 057 | 2023-04-25 | 2023-05-04
| Act 062 | 2023-04-30 | 2023-05-08
| Act 064 | 2023-05-01 | 2023-05-09
| Act 071 | 2023-05-07 | 2023-05-12
| Act 074 | 2023-05-10 | 2023-05-20
| Act 077 | 2023-05-13 | 2023-05-20
| Act 081 | 2023-05-16 | 2023-05-26
| Act 082 | 2023-05-16 | 2023-05-20
| Act 091 | 2023-05-25 | 2023-05-28
| Act 097 | 2023-06-01 | 2023-06-04
| Act 099 | 2023-06-03 | 2023-06-06
Development |  | 2023-03-07 | 2023-05-27
| Act 007 | 2023-03-07 | 2023-03-15
| Act 011 | 2023-03-08 | 2023-03-18
| Act 017 | 2023-03-15 | 2023-03-19
| Act 021 | 2023-03-18 | 2023-03-23
| Act 023 | 2023-03-19 | 2023-03-26
| Act 031 | 2023-03-27 | 2023-04-06
| Act 036 | 2023-03-30 | 2023-04-07
| Act 045 | 2023-04-08 | 2023-04-14
| Act 054 | 2023-04-21 | 2023-04-27
| Act 058 | 2023-04-25 | 2023-05-01
| Act 059 | 2023-04-25 | 2023-05-01
| Act 063 | 2023-04-30 | 2023-05-03
| Act 065 | 2023-05-01 | 2023-05-08
| Act 070 | 2023-05-05 | 2023-05-08
| Act 083 | 2023-05-17 | 2023-05-25
| Act 085 | 2023-05-18 | 2023-05-27
| Act 086 | 2023-05-19 | 2023-05-27
Requirements |  | 2023-03-03 | 2023-06-09
| Act 003 | 2023-03-03 | 2023-03-07
| Act 004 | 2023-03-04 | 2023-03-14
| Act 009 | 2023-03-07 | 2023-03-11
| Act 010 | 2023-03-08 | 2023-03-13
| Act 014 | 2023-03-11 | 2023-03-15
| Act 018 | 2023-03-16 | 2023-03-22
| Act 020 | 2023-03-18 | 2023-03-24
| Act 034 | 2023-03-29 | 2023-04-06
| Act 035 | 2023-03-29 | 2023-04-06
| Act 037 | 2023-04-01 | 2023-04-04
| Act 040 | 2023-04-03 | 2023-04-11
| Act 043 | 2023-04-05 | 2023-04-11
| Act 048 | 2023-04-11 | 2023-04-15
| Act 056 | 2023-04-25 | 2023-04-29
| Act 061 | 2023-04-28 | 2023-05-03
| Act 067 | 2023-05-02 | 2023-05-10
| Act 072 | 2023-05-07 | 2023-05-13
| Act 078 | 2023-05-13 | 2023-05-22
| Act 084 | 2023-05-18 | 2023-05-26
| Act 087 | 2023-05-20 | 2023-05-28
| Act 090 | 2023-05-23 | 2023-05-28
| Act 092 | 2023-05-27 | 2023-06-05
| Act 093 | 2023-05-29 | 2023-06-02
| Act 094 | 2023-05-30 | 2023-06-03
| Act 095 | 2023-05-31 | 2023-06-08
| Act 100 | 2023-06-05 | 2023-06-09
Testing |  | 2023-03-07 | 2023-06-09
| Act 008 | 2023-03-07 | 2023-03-16
| Act 015 | 2023-03-13 | 2023-03-23
| Act 024 | 2023-03-19 | 2023-03-24
| Act 026 | 2023-03-23 | 2023-03-30
| Act 029 | 2023-03-25 | 2023-03-31
| Act 030 | 2023-03-27 | 2023-04-04
| Act 033 | 2023-03-29 | 2023-04-04
| Act 042 | 2023-04-03 | 2023-04-09
| Act 046 | 2023-04-09 | 2023-04-19
| Act 051 | 2023-04-15 | 2023-04-22
| Act 055 | 2023-04-23 | 2023-04-26
| Act 066 | 2023-05-02 | 2023-05-06
| Act 073 | 2023-05-09 | 2023-05-17
| Act 080 | 2023-05-15 | 2023-05-21
| Act 089 | 2023-05-23 | 2023-05-26
| Act 098 | 2023-06-01 | 2023-06-09
Grand Total |  | 2023-03-01 | 2023-06-09
Formulas:
Start Date = [Scenario]-[minus]

## Design
Colors |  | white
Fonts
Headings | Lora
Subheadings | Roboto
Body | Calibri
Icons
Logo