## Calculations
Category | Activity | Min of Start Date | Max of End Date | Scenario
Deployment |  | 2023-03-01 | 2023-06-04 | Today's Date | minus | Start Date | Start Date (value)
| Act 002 | 2023-03-01 | 2023-03-11 | 2023-05-01 | 14 | 2023-04-17 | 2023-04-17
| Act 012 | 2023-03-08 | 2023-03-14
| Act 016 | 2023-03-13 | 2023-03-19
| Act 019 | 2023-03-17 | 2023-03-22
| Act 022 | 2023-03-18 | 2023-03-21
| Act 025 | 2023-03-21 | 2023-03-25
| Act 027 | 2023-03-24 | 2023-03-28
| Act 028 | 2023-03-24 | 2023-04-02
| Act 032 | 2023-03-29 | 2023-04-02
| Act 038 | 2023-04-02 | 2023-04-05
| Act 044 | 2023-04-07 | 2023-04-15
| Act 049 | 2023-04-13 | 2023-04-19
| Act 060 | 2023-04-26 | 2023-05-06
| Act 068 | 2023-05-04 | 2023-05-13
| Act 069 | 2023-05-05 | 2023-05-12
| Act 075 | 2023-05-11 | 2023-05-14
| Act 076 | 2023-05-12 | 2023-05-19
| Act 079 | 2023-05-14 | 2023-05-19
| Act 088 | 2023-05-22 | 2023-05-26
| Act 096 | 2023-06-01 | 2023-06-04
Design |  | 2023-03-01 | 2023-06-06
| Act 001 | 2023-03-01 | 2023-03-04
| Act 005 | 2023-03-05 | 2023-03-12
| Act 006 | 2023-03-06 | 2023-03-16
| Act 013 | 2023-03-09 | 2023-03-13
| Act 039 | 2023-04-03 | 2023-04-09
| Act 041 | 2023-04-03 | 2023-04-06
| Act 047 | 2023-04-10 | 2023-04-13
| Act 050 | 2023-04-14 | 2023-04-23
| Act 052 | 2023-04-17 | 2023-04-23
| Act 053 | 2023-04-19 | 2023-04-24
| Act 057 | 2023-04-25 | 2023-05-04
| Act 062 | 2023-04-30 | 2023-05-08
| Act 064 | 2023-05-01 | 2023-05-09
| Act 071 | 2023-05-07 | 2023-05-12
| Act 074 | 2023-05-10 | 2023-05-20
| Act 077 | 2023-05-13 | 2023-05-20
| Act 081 | 2023-05-16 | 2023-05-26
| Act 082 | 2023-05-16 | 2023-05-20
| Act 091 | 2023-05-25 | 2023-05-28
| Act 097 | 2023-06-01 | 2023-06-04
| Act 099 | 2023-06-03 | 2023-06-06
Development |  | 2023-03-07 | 2023-05-27
| Act 007 | 2023-03-07 | 2023-03-15
| Act 011 | 2023-03-08 | 2023-03-18
| Act 017 | 2023-03-15 | 2023-03-19
| Act 021 | 2023-03-18 | 2023-03-23
| Act 023 | 2023-03-19 | 2023-03-26
| Act 031 | 2023-03-27 | 2023-04-06
| Act 036 | 2023-03-30 | 2023-04-07
| Act 045 | 2023-04-08 | 2023-04-14
| Act 054 | 2023-04-21 | 2023-04-27
| Act 058 | 2023-04-25 | 2023-05-01
| Act 059 | 2023-04-25 | 2023-05-01
| Act 063 | 2023-04-30 | 2023-05-03
| Act 065 | 2023-05-01 | 2023-05-08
| Act 070 | 2023-05-05 | 2023-05-08
| Act 083 | 2023-05-17 | 2023-05-25
| Act 085 | 2023-05-18 | 2023-05-27
| Act 086 | 2023-05-19 | 2023-05-27
Requirements |  | 2023-03-03 | 2023-06-09
| Act 003 | 2023-03-03 | 2023-03-07
| Act 004 | 2023-03-04 | 2023-03-14
| Act 009 | 2023-03-07 | 2023-03-11
| Act 010 | 2023-03-08 | 2023-03-13
| Act 014 | 2023-03-11 | 2023-03-15
| Act 018 | 2023-03-16 | 2023-03-22
| Act 020 | 2023-03-18 | 2023-03-24
| Act 034 | 2023-03-29 | 2023-04-06
| Act 035 | 2023-03-29 | 2023-04-06
| Act 037 | 2023-04-01 | 2023-04-04
| Act 040 | 2023-04-03 | 2023-04-11
| Act 043 | 2023-04-05 | 2023-04-11
| Act 048 | 2023-04-11 | 2023-04-15
| Act 056 | 2023-04-25 | 2023-04-29
| Act 061 | 2023-04-28 | 2023-05-03
| Act 067 | 2023-05-02 | 2023-05-10
| Act 072 | 2023-05-07 | 2023-05-13
| Act 078 | 2023-05-13 | 2023-05-22
| Act 084 | 2023-05-18 | 2023-05-26
| Act 087 | 2023-05-20 | 2023-05-28
| Act 090 | 2023-05-23 | 2023-05-28
| Act 092 | 2023-05-27 | 2023-06-05
| Act 093 | 2023-05-29 | 2023-06-02
| Act 094 | 2023-05-30 | 2023-06-03
| Act 095 | 2023-05-31 | 2023-06-08
| Act 100 | 2023-06-05 | 2023-06-09
Testing |  | 2023-03-07 | 2023-06-09
| Act 008 | 2023-03-07 | 2023-03-16
| Act 015 | 2023-03-13 | 2023-03-23
| Act 024 | 2023-03-19 | 2023-03-24
| Act 026 | 2023-03-23 | 2023-03-30
| Act 029 | 2023-03-25 | 2023-03-31
| Act 030 | 2023-03-27 | 2023-04-04
| Act 033 | 2023-03-29 | 2023-04-04
| Act 042 | 2023-04-03 | 2023-04-09
| Act 046 | 2023-04-09 | 2023-04-19
| Act 051 | 2023-04-15 | 2023-04-22
| Act 055 | 2023-04-23 | 2023-04-26
| Act 066 | 2023-05-02 | 2023-05-06
| Act 073 | 2023-05-09 | 2023-05-17
| Act 080 | 2023-05-15 | 2023-05-21
| Act 089 | 2023-05-23 | 2023-05-26
| Act 098 | 2023-06-01 | 2023-06-09
Grand Total |  | 2023-03-01 | 2023-06-09
Formulas:
Start Date = [Scenario]-[minus]

## Teams-data
Person | Team
Bruce Wayne | Code Wizards
James Gordon | Code Wizards
Alfred Pennyworth | Code Wizards
Bane | Code Wizards
Selina Kyle | Code Wizards
Harley Quinn | Cyber Surfers
Barbara Gordon | Cyber Surfers
Richard Grayson | Cyber Surfers
Joker | Cyber Surfers
Lucius Fox | Cyber Surfers

## Activity-data
Activity | Category | Owner | Start Date | End Date | % Done
Act 001 | Design | Barbara Gordon | 2023-03-01 | 2023-03-04 | 59%
Act 002 | Deployment | Harley Quinn | 2023-03-01 | 2023-03-11 | 70%
Act 003 | Requirements | Richard Grayson | 2023-03-03 | 2023-03-07 | 62%
Act 004 | Requirements | Selina Kyle | 2023-03-04 | 2023-03-14 | 60%
Act 005 | Design | Richard Grayson | 2023-03-05 | 2023-03-12 | 75%
Act 006 | Design | Bruce Wayne | 2023-03-06 | 2023-03-16 | 100%
Act 007 | Development | Barbara Gordon | 2023-03-07 | 2023-03-15 | 78%
Act 008 | Testing | Barbara Gordon | 2023-03-07 | 2023-03-16 | 61%
Act 009 | Requirements | Alfred Pennyworth | 2023-03-07 | 2023-03-11 | 100%
Act 010 | Requirements | Alfred Pennyworth | 2023-03-08 | 2023-03-13 | 27%
Act 011 | Development | Selina Kyle | 2023-03-08 | 2023-03-18 | 100%
Act 012 | Deployment | Joker | 2023-03-08 | 2023-03-14 | 88%
Act 013 | Design | Lucius Fox | 2023-03-09 | 2023-03-13 | 51%
Act 014 | Requirements | Harley Quinn | 2023-03-11 | 2023-03-15 | 95%
Act 015 | Testing | Bane | 2023-03-13 | 2023-03-23 | 70%
Act 016 | Deployment | Selina Kyle | 2023-03-13 | 2023-03-19 | 99%
Act 017 | Development | Barbara Gordon | 2023-03-15 | 2023-03-19 | 100%
Act 018 | Requirements | Harley Quinn | 2023-03-16 | 2023-03-22 | 100%
Act 019 | Deployment | Joker | 2023-03-17 | 2023-03-22 | 100%
Act 020 | Requirements | Alfred Pennyworth | 2023-03-18 | 2023-03-24 | 83%
Act 021 | Development | Alfred Pennyworth | 2023-03-18 | 2023-03-23 | 100%
Act 022 | Deployment | Harley Quinn | 2023-03-18 | 2023-03-21 | 44%
Act 023 | Development | James Gordon | 2023-03-19 | 2023-03-26 | 100%
Act 024 | Testing | Lucius Fox | 2023-03-19 | 2023-03-24 | 88%
Act 025 | Deployment | James Gordon | 2023-03-21 | 2023-03-25 | 100%
Act 026 | Testing | Selina Kyle | 2023-03-23 | 2023-03-30 | 70%
Act 027 | Deployment | James Gordon | 2023-03-24 | 2023-03-28 | 100%
Act 028 | Deployment | Bane | 2023-03-24 | 2023-04-02 | 79%
Act 029 | Testing | Bruce Wayne | 2023-03-25 | 2023-03-31 | 100%
Act 030 | Testing | Richard Grayson | 2023-03-27 | 2023-04-04 | 100%
Act 031 | Development | Bane | 2023-03-27 | 2023-04-06 | 76%
Act 032 | Deployment | Joker | 2023-03-29 | 2023-04-02 | 22%
Act 033 | Testing | Alfred Pennyworth | 2023-03-29 | 2023-04-04 | 67%
Act 034 | Requirements | Selina Kyle | 2023-03-29 | 2023-04-06 | 100%
Act 035 | Requirements | James Gordon | 2023-03-29 | 2023-04-06 | 100%
Act 036 | Development | Bane | 2023-03-30 | 2023-04-07 | 100%
Act 037 | Requirements | Richard Grayson | 2023-04-01 | 2023-04-04 | 100%
Act 038 | Deployment | Bane | 2023-04-02 | 2023-04-05 | 100%
Act 039 | Design | Lucius Fox | 2023-04-03 | 2023-04-09 | 100%
Act 040 | Requirements | Lucius Fox | 2023-04-03 | 2023-04-11 | 27%
Act 041 | Design | Richard Grayson | 2023-04-03 | 2023-04-06 | 100%
Act 042 | Testing | James Gordon | 2023-04-03 | 2023-04-09 | 100%
Act 043 | Requirements | Barbara Gordon | 2023-04-05 | 2023-04-11 | 84%
Act 044 | Deployment | Richard Grayson | 2023-04-07 | 2023-04-15 | 45%
Act 045 | Development | Bruce Wayne | 2023-04-08 | 2023-04-14 | 92%
Act 046 | Testing | Bane | 2023-04-09 | 2023-04-19 | 66%
Act 047 | Design | James Gordon | 2023-04-10 | 2023-04-13 | 65%
Act 048 | Requirements | Bruce Wayne | 2023-04-11 | 2023-04-15 | 100%
Act 049 | Deployment | Barbara Gordon | 2023-04-13 | 2023-04-19 | 79%
Act 050 | Design | Joker | 2023-04-14 | 2023-04-23 | 100%
Act 051 | Testing | Alfred Pennyworth | 2023-04-15 | 2023-04-22 | 96%
Act 052 | Design | Bruce Wayne | 2023-04-17 | 2023-04-23 | 100%
Act 053 | Design | Lucius Fox | 2023-04-19 | 2023-04-24 | 59%
Act 054 | Development | Barbara Gordon | 2023-04-21 | 2023-04-27 | 100%
Act 055 | Testing | Barbara Gordon | 2023-04-23 | 2023-04-26 | 21%
Act 056 | Requirements | Joker | 2023-04-25 | 2023-04-29 | 96%
Act 057 | Design | Alfred Pennyworth | 2023-04-25 | 2023-05-04 | 62%
Act 058 | Development | Selina Kyle | 2023-04-25 | 2023-05-01 | 72%
Act 059 | Development | Harley Quinn | 2023-04-25 | 2023-05-01 | 45%
Act 060 | Deployment | Richard Grayson | 2023-04-26 | 2023-05-06 | 25%
Act 061 | Requirements | James Gordon | 2023-04-28 | 2023-05-03 | 87%
Act 062 | Design | Bane | 2023-04-30 | 2023-05-08 | 100%
Act 063 | Development | Lucius Fox | 2023-04-30 | 2023-05-03 | 0%
Act 064 | Design | Lucius Fox | 2023-05-01 | 2023-05-09 | 0%
Act 065 | Development | Alfred Pennyworth | 2023-05-01 | 2023-05-08 | 0%
Act 066 | Testing | Richard Grayson | 2023-05-02 | 2023-05-06 | 0%
Act 067 | Requirements | Barbara Gordon | 2023-05-02 | 2023-05-10 | 0%
Act 068 | Deployment | Joker | 2023-05-04 | 2023-05-13 | 0%
Act 069 | Deployment | Joker | 2023-05-05 | 2023-05-12 | 0%
Act 070 | Development | James Gordon | 2023-05-05 | 2023-05-08 | 0%
Act 071 | Design | Bruce Wayne | 2023-05-07 | 2023-05-12 | 0%
Act 072 | Requirements | Richard Grayson | 2023-05-07 | 2023-05-13 | 0%
Act 073 | Testing | Selina Kyle | 2023-05-09 | 2023-05-17 | 0%
Act 074 | Design | Bane | 2023-05-10 | 2023-05-20 | 0%
Act 075 | Deployment | Selina Kyle | 2023-05-11 | 2023-05-14 | 0%
Act 076 | Deployment | Barbara Gordon | 2023-05-12 | 2023-05-19 | 0%
Act 077 | Design | Richard Grayson | 2023-05-13 | 2023-05-20 | 0%
Act 078 | Requirements | Selina Kyle | 2023-05-13 | 2023-05-22 | 0%
Act 079 | Deployment | Barbara Gordon | 2023-05-14 | 2023-05-19 | 0%
Act 080 | Testing | Barbara Gordon | 2023-05-15 | 2023-05-21 | 0%
Act 081 | Design | Harley Quinn | 2023-05-16 | 2023-05-26 | 0%
Act 082 | Design | Richard Grayson | 2023-05-16 | 2023-05-20 | 0%
Act 083 | Development | Barbara Gordon | 2023-05-17 | 2023-05-25 | 0%
Act 084 | Requirements | Alfred Pennyworth | 2023-05-18 | 2023-05-26 | 0%
Act 085 | Development | James Gordon | 2023-05-18 | 2023-05-27 | 0%
Act 086 | Development | Richard Grayson | 2023-05-19 | 2023-05-27 | 0%
Act 087 | Requirements | Bane | 2023-05-20 | 2023-05-28 | 0%
Act 088 | Deployment | Bane | 2023-05-22 | 2023-05-26 | 0%
Act 089 | Testing | Lucius Fox | 2023-05-23 | 2023-05-26 | 0%
Act 090 | Requirements | Barbara Gordon | 2023-05-23 | 2023-05-28 | 0%
Act 091 | Design | Joker | 2023-05-25 | 2023-05-28 | 0%
Act 092 | Requirements | Bane | 2023-05-27 | 2023-06-05 | 0%
Act 093 | Requirements | James Gordon | 2023-05-29 | 2023-06-02 | 0%
Act 094 | Requirements | Lucius Fox | 2023-05-30 | 2023-06-03 | 0%
Act 095 | Requirements | Selina Kyle | 2023-05-31 | 2023-06-08 | 0%
Act 096 | Deployment | Barbara Gordon | 2023-06-01 | 2023-06-04 | 0%
Act 097 | Design | Lucius Fox | 2023-06-01 | 2023-06-04 | 0%
Act 098 | Testing | Lucius Fox | 2023-06-01 | 2023-06-09 | 0%
Act 099 | Design | Barbara Gordon | 2023-06-03 | 2023-06-06 | 0%
Act 100 | Requirements | James Gordon | 2023-06-05 | 2023-06-09 | 0%

## Issue-data
Issue | Assigned to | Priority | Date opened | Date Closed
Keyboard scanner won't open up | Bruce Wayne | High | 2023-04-02
Server email folder not responding | Harley Quinn | High | 2023-04-03
Keyboard scanner not responding | Joker | High | 2023-04-04
Keyboard scanner won't open up | Alfred Pennyworth | Low | 2023-04-05 | 2021-04-08
Keyboard scanner not responding | Richard Grayson | Low | 2023-04-05
Missing monitoring meter | Lucius Fox | Low | 2023-04-06
Server email folder are not working | Bruce Wayne | Low | 2023-04-07
User specifications are not working | James Gordon | Low | 2023-04-07
Missing interaction effects | Joker | High | 2023-04-08
Battery status screen not responding | Selina Kyle | High | 2023-04-09
Broken template files | Lucius Fox | Low | 2023-04-11 | 2021-04-14
Closed template files | Harley Quinn | Low | 2023-04-12
Keyboard scanner won't open up | James Gordon | Low | 2023-04-14
User specifications is blended | Joker | Low | 2023-04-17
Missing interaction effects | Alfred Pennyworth | High | 2023-04-17
Closed expansion slots | Lucius Fox | High | 2023-04-18
Missing template files | James Gordon | Low | 2023-04-19
Closed expansion slots | Lucius Fox | Low | 2023-04-19
Battery status screen are not working | Bruce Wayne | Low | 2023-04-20
Closed monitoring meter | Joker | Low | 2023-04-22
Closed expansion slots | Barbara Gordon | Low | 2023-04-25
Broken expansion slots | James Gordon | High | 2023-04-26
Missing expansion slots | Bane | High | 2023-04-27
Slow template files | Richard Grayson | Low | 2023-04-28
Broken template files | James Gordon | High | 2023-04-30